## GOH 16M,16G.16H
No | Job Description GOH 16M/16G/16H | Duration (hrs)
Remove / Disassembly
1 | Clean up machine | 4
2 | Performance test Machhine | 6
3 | Stand up machine + Preentry | 4
4 | Remove all Tyres | 4
5 | Remove blade gp | 4
6 | Remove Circle Drive | 4
7 | Remove Swivel | 1
8 | Remove Side & Center shift Cyl | 1
9 | Remove Hoist Cyl 2x | 3
10 | Remove drawbar & circle | 3
11 | Remove engine hood & Radiator hood | 3
12 | Remove hydraulic hose / lines | 3
13 | Remove Radiator Gp | 3
14 | Remove Fuel Lines & Fuel Tank | 6
15 | Remove air intake & exhaust Gp | 6
16 | Remove Electrict system (harness, Lamps, cable etc) | 6
17 | Remove Drive shaft - Upper | 6
18 | Remove Drive shaft - Lower | 6
19 | Remove Engine Gp | 24
20 | Remove Trasmission Gp | 24
21 | Remove Front Axle Gp | 6
22 | Remove Articulation cyl 2x | 3
23 | Remove RH Drive Chain 2X | 3
24 | Remove RH Service Brake 2x | 3
25 | Remove Slack Adjuster LH & RH | 3
26 | Remove RH Tandem | 1
27 | Remove LH Drive chain 2x | 1
28 | Remove LH Service brake 2x | 1
29 | Remove LH Tandem | 1
30 | Remove Final drive LH | 6
31 | Remove Final drive RH | 4
32 | Remove Differential | 4
33 | Remove Cabin Gp | 4
34 | Remove Hydraulic tank | 4
35 | Remove Hyd Control valve | 4
36 | Remove Steering valve | 4
37 | Remove Blade sideshift | 1
38 | Remove Tip Cylinder | 1
39 | Remove Ripper lift | 1
40 | Disconnect Front Frame & Rear Frame | 48
41 | Disconnect Ripper frame | 2
42 | Remove Brake Accumulator 2x | 48
43 | Remove Hyd Accumulator | 24
44 | Remove secondary steering pump | 16
45 | Remove Emergency Steering pump | 17
46 | Remove Afftercooler | 18
47 | Remove Manifodl Brake | 19
48 | Remove manifold Steering & pilot | 4
49 | Remove Hyd Pump | 16
50 | Remove Steering pump | 16
Recondition Component
51 | Completed engine (repl/ install minor comp, covers & guards) | 48
52 | Inspect Radiator - recondisi Radiator | 48
53 | Recondition Cabin | 48
54 | Rebearing Drive shaft | 48
55 | Inspect & rekondition LH Tandem | 48
56 | Inspect & rekondition RH Tandem | 48
57 | Recondition Hydraulic Tank | 48
58 | Recondition Fuel Tank | 48
59 | Recondition/rebearing circle & drawbar & blade | 48
60 | Recondition/rebearing ripper frame | 48
Outside works
60 | PT. TSP - NDT Frame | 4
61 | PT. TSP - Repair Frame | 6
62 | PT. SEN - Air conditioner | 6
Outside works
63 | Clean up Main frame, Axle Housing hoods & components | 8
64 | Rebearing oscilating hitch | 4
65 | Rebearing Front & Rear Frame | 2
66 | Connecting Rear & Front Frame | 6
67 | Install Articulation 2x | 4
68 | Install Ripper Frame | 4
69 | Install Ripper Cyl | 4
70 | Install Hydraulic hose | 6
71 | Install Electric system (harness, lamp & cables, etc) | 8
72 | Install Hydraulic Pump | 10
73 | Install Brake Pump | 3
74 | Install Engine Gp | 2
75 | Install Transmission | 2
76 | Install Differential Gp | 2
77 | Install LH Final drive | 2
78 | Install RH Final drive | 2
79 | Install LH Service Brake 2x | 2
80 | Install RH service Brake 2X | 2
81 | Install LH Tandem | 2
82 | Install RH Tandem | 2
83 | Install Front Axle | 2
84 | Install Circle & Drawbar | 2
85 | Install Drive shaft 2x | 2
86 | Install Lift cylinder 2x | 2
87 | Install Centershift cyl | 2
88 | Install Circle Drive | 2
89 | Recondisi & Install Swivel | 2
90 | Install Aftercooler | 2
91 | Install Radiator Gp & cooling lines | 2
92 | Install Hydraulic tank | 2
93 | Install Fuel Tank | 2
94 | Install Blade gp | 2
95 | Install Blade sideshift cyl | 2
96 | Install Blade Tip Cyl | 2
97 | Install Hyd control valve | 2
98 | Install steering valve | 2
99 | Install Slack Adjuster 2x | 1
100 | Install fuel hose & lines | 2
101 | Install Air intake & Exhaust | 2
102 | Install Secondary pump | 1
103 | Install Accumulator hyd & Brake | 2
104 | Install Emergency pump | 1
105 | Install manifold Brake | 5
106 | Install Manifold steering & pilot | 12
107 | Install Cabin & Completed | 3
108 | Install Engine hood & radiator hood | 4
109 | Install All Tyres | 6
110 | Completed machine | 36
Performace test
111 | Performance test | 24
112 | Install guard and hoods | 2
113 | Prerelease | 0.5

## GOH 24M,24H
No | Job Description GOH 24H/24M | Duration (hrs)
Remove / Disassembly
1 | Clean up machine | 4
2 | Performance test Machhine | 6
3 | Stand up machine + Preentry | 4
4 | Remove all Tyres | 4
5 | Remove blade gp | 4
6 | Remove Circle Drive | 4
7 | Remove Swivel | 1
8 | Remove Side & Center shift Cyl | 1
9 | Remove Hoist Cyl 2x | 3
10 | Remove drawbar & circle | 3
11 | Remove engine hood & Radiator hood | 3
12 | Remove hydraulic hose / lines | 3
13 | Remove Radiator Gp | 3
14 | Remove Fuel Lines & Fuel Tank | 6
15 | Remove air intake & exhaust Gp | 6
16 | Remove Electrict system (harness, Lamps, cable etc) | 6
17 | Remove Drive shaft - Upper | 6
18 | Remove Drive shaft - Lower | 6
19 | Remove Engine Gp | 24
20 | Remove Trasmission Gp | 24
21 | Remove Front Axle Gp | 6
22 | Remove Articulation cyl 2x | 3
23 | Remove RH Drive Chain 2X | 3
24 | Remove RH Service Brake 2x | 3
25 | Remove Slack Adjuster LH & RH | 3
26 | Remove RH Tandem | 1
27 | Remove LH Drive chain 2x | 1
28 | Remove LH Service brake 2x | 1
29 | Remove LH Tandem | 1
30 | Remove Final drive LH | 6
31 | Remove Final drive RH | 4
32 | Remove Differential | 4
33 | Remove Cabin Gp | 4
34 | Remove Hydraulic tank | 4
35 | Remove Hyd Control valve | 4
36 | Remove Steering valve | 4
37 | Remove Blade sideshift | 1
38 | Remove Tip Cylinder | 1
39 | Remove Ripper lift | 1
40 | Disconnect Front Frame & Rear Frame | 48
41 | Disconnect Ripper frame | 2
42 | Remove Brake Accumulator 2x | 48
43 | Remove Hyd Accumulator | 24
44 | Remove secondary steering pump | 16
45 | Remove Emergency Steering pump | 17
46 | Remove Afftercooler | 18
47 | Remove Manifodl Brake | 19
48 | Remove manifold Steering & pilot | 4
49 | Remove Hyd Pump | 16
50 | Remove Steering pump | 16
Recondition Component
51 | Completed engine (repl/ install minor comp, covers & guards) | 48
52 | Inspect Radiator - recondisi Radiator | 48
53 | Recondition Cabin | 48
54 | Rebearing Drive shaft | 48
55 | Inspect & rekondition LH Tandem | 48
56 | Inspect & rekondition RH Tandem | 48
57 | Recondition Hydraulic Tank | 48
58 | Recondition Fuel Tank | 48
59 | Recondition/rebearing circle & drawbar & blade | 48
60 | Recondition/rebearing ripper frame | 48
Outside works
61 | PT. TSP - NDT Frame | 4
62 | PT. TSP - Repair Frame | 6
63 | PT. SHB - Painting
64 | PT. SEN - Air conditioner | 6
Outside works
65 | Clean up Main frame, Axle Housing hoods & components | 8
66 | Rebearing oscilating hitch | 4
67 | Rebearing Front & Rear Frame | 36
68 | Connecting Rear & Front Frame | 6
69 | Install Articulation 2x | 4
70 | Install Ripper Frame | 4
71 | Install Ripper Cyl | 4
72 | Install Hydraulic hose | 6
73 | Install Electric system (harness, lamp & cables, etc) | 8
74 | Install Hydraulic Pump | 10
75 | Install Brake Pump | 3
76 | Install Engine Gp | 2
77 | Install Transmission | 2
78 | Install Differential Gp | 2
79 | Install LH Final drive | 2
80 | Install RH Final drive | 2
81 | Install LH Service Brake 2x | 2
82 | Install RH service Brake 2X | 2
83 | Install LH Tandem | 2
84 | Install RH Tandem | 2
85 | Install Front Axle | 2
86 | Install Circle & Drawbar | 2
87 | Install Drive shaft 2x | 2
88 | Install Lift cylinder 2x | 2
89 | Install Centershift cyl | 2
90 | Install Circle Drive | 2
91 | Recondisi & Install Swivel | 2
92 | Install Aftercooler | 2
93 | Install Radiator Gp & cooling lines | 2
94 | Install Hydraulic tank | 2
95 | Install Fuel Tank | 2
96 | Install Blade gp | 2
97 | Install Blade sideshift cyl | 2
98 | Install Blade Tip Cyl | 2
99 | Install Hyd control valve | 2
100 | Install steering valve | 2
101 | Install Slack Adjuster 2x | 1
102 | Install fuel hose & lines | 2
103 | Install Air intake & Exhaust | 2
104 | Install Secondary pump | 1
105 | Install Accumulator hyd & Brake | 2
106 | Install Emergency pump | 1
107 | Install manifold Brake | 5
108 | Install Manifold steering & pilot | 12
109 | Install Cabin & Completed | 3
110 | Install Engine hood & radiator hood | 4
111 | Install All Tyres | 6
112 | Completed machine | 36
Performace test
113 | Performance test | 24
114 | Install guard and hoods | 2
115 | Prerelease | 0.5

## GOH OHT 785
No | Job Description GOH OHT 785 | Duration (hrs)
Remove / Disassembly
1 | Clean up machine | 2.5
2 | Take data PSRPT & Performance test | 5
3 | Stand up machine | 4
4 | Remove engine Hood & Radiator guards / hood | 10
5 | Remove Air intake & Exhaust lines | 6
6 | Remove Fuel lines | 2
7 | Remove Main Drive Shaft | 2
8 | Remove pump Drive Shaft | 1
9 | Remove hose & lines | 20
10 | Remove Electric system | 15
11 | Remove Radiator & cooling lines | 6
12 | Remove engine & T/C | 6
13 | Remove Cabin | 4
14 | Remove Mirror, flatform, Handraill & Fender | 12
15 | Remove Front tyre 2 ea | 4
16 | Remove Front LH Suspension Gp | 4
17 | Remove Front RH Suspension Gp | 4
18 | Remove Pump drive | 3
19 | Remove Steering Tank | 2
20 | Remove Air Tank & lines | 2
21 | Remove transmission oil cooler | 4
22 | Remove Rear Tyres | 8
23 | Remove LH & RH Rear Suspension | 4
24 | Remove Rear Axle Shaft LH & RH | 1
25 | Remove LH & RH Final drive | 6
26 | Remove Transmission GP | 4
27 | Remove Rear Axle | 6
28 | Remove Hoist LH & RH | 6
29 | Remove Hyd Tank | 3
30 | Remove Fuel tank | 3
31 | Remove Steering Linkage | 4
32 | Remove Steering cyl LH & RH | 4
33 | Steering valves | 2
34 | Remove acculumator | 2
35 | Brake valves, AETA | 2
36 | Remove Hyd Control valves | 2
37 | Remove front Brake oil cooler | 2
38 | Remove Brake Slack adjuster | 2
39 | Remove Brake airover hyd cyl 3x | 2
40 | Remove Ladders | 4
41 | Clean up main frame | 4
Recondition Component
42 | Discon & connect Transmission & Differential | 3
43 | Recondition Hyd & Trans tank | 6
44 | Recondition Steering Tank | 4
45 | Recondition Fuel Tank | 4
Assemble Machine
46 | Reposition & Stand up main Frame at wshop | 3
47 | Install bracket, mountings & Rebearing Main Frame | 12
48 | Overhaull Steering Linkage | 8
49 | Install LH & RH Steering cylinder | 4
50 | Install Hyd hose and lines | 48
51 | Install T/Conventer to Engine - completed engine | 24
52 | Install engine Gp To Main Frame | 12
53 | Completed Radiator & Install to Machine | 12
54 | Rebearing A-frame & Install to Rear Axle gp | 18
55 | Install Rear Axle housing | 6
56 | Install LH & RH rear Suspension | 4
57 | Install LH & RH Final drive | 6
58 | Install transmission Gp | 4
59 | Install Rear Axle Shaft LH & RH | 2
60 | Install Rear Tyres | 4
61 | Install Pump to Pump drive & install pump drive Gp to Main Frame | 4
62 | Remove Install Front hub to RF & LF Suspension | 12
63 | Install RH Front Suspension Gp to frame & completed | 6
64 | Install LH Front Suspension Gp to frame & completed | 6
65 | Install Front Tyre LH & RH | 5
66 | Install Fender, catwalk, Hood & guards | 12
67 | Install Air induction & exhaust | 12
68 | Install Hyd & Steering Tank | 4
69 | Install Electric system | 36
70 | Install Fuel tank | 2
71 | Install Fuel lines | 4
72 | Install main drive shaft | 2
73 | Install Pump drive shaft | 1
74 | Install Hyd & Stering Valves | 2
75 | Install Brake Valve & AETA Vlv | 2
76 | Install Accumulator Steering | 4
77 | Install Front Brake & Trans oil cooler | 2
78 | Install Air tank & lines | 4
79 | Install Cabin & Completed | 24
80 | Install Slack Adjuster 2 x | 2
81 | Install Brake airover hyd cyl 3x | 2
82 | Install Mirror, flatform & Handraill | 8
83 | Install Ladders | 4
84 | Install Hoist LH & RH | 4
85 | Completed Machine (include refill oils) | 48
86 | Repair frame, Guard, handrail etc by TSP | 60
87 | Painting Machine - PT. SHB | 36
88 | GOH Air Conditioner - PT. SEN | 36
89 | GOH Fire supp & Autolube - PT INTECS | 40
Performace test
90 | Performance test | 36
91 | Install guard and hoods | 3
92 | Prerelease | 0.5

## GOH OHT 789
No | Job Description GOH OHT 789 | Duration (hrs)
Remove / Disassembly
1 | Clean up machine | 2.5
2 | Take data PSRPT & Performance test | 2
3 | Stand up machine | 4
4 | Remove engine Hood & Radiator guards / hood | 10
5 | Remove Air intake & Exhaust lines | 6
6 | Remove Fuel lines | 2
7 | Remove Main Drive Shaft | 2
8 | Remove pump Drive Shaft | 1
9 | Remove hose & lines | 20
10 | Remove Electric system | 15
11 | Remove Radiator & cooling lines | 6
12 | Remove engine & T/C | 6
13 | Remove Cabin | 4
14 | Remove Mirror, flatform, Handraill & Fender | 12
15 | Remove Front tyre 2 ea | 4
16 | Remove Front LH Suspension Gp | 4
17 | Remove Front RH Suspension Gp | 4
18 | Remove Pump drive | 3
19 | Remove Steering Tank | 2
20 | Remove Air Tank & lines | 2
21 | Remove transmission oil cooler | 4
22 | Remove Rear Tyres | 4
23 | Remove LH & RH Rear Suspension | 4
24 | Remove Rear Axle Shaft LH & RH | 1
25 | Remove LH & RH Final drive | 6
26 | Remove Transmission GP | 4
27 | Remove Rear Axle | 6
28 | Remove Hoist LH & RH | 6
29 | Remove Hyd Tank | 3
30 | Remove Fuel tank | 3
31 | Remove Steering Linkage | 4
32 | Remove Steering cyl LH & RH | 4
33 | Steering valves | 2
34 | Remove acculumator | 2
35 | Brake valves, AETA | 2
36 | Remove Hyd Control valves | 2
37 | Remove front Brake oil cooler | 2
38 | Remove Brake Slack adjuster | 2
39 | Remove Brake airover hyd cyl 3x | 2
40 | Remove Ladders | 4
41 | Clean up main frame | 4
Recondition Component
42 | Discon & connect Transmission & Differential | 3
43 | Recondition Hyd & Trans tank | 6
44 | Recondition Steering Tank | 4
45 | Recondition Fuel Tank | 4
Assemble Machine
46 | Reposition & Stand up main Frame at wshop | 3
47 | Install bracket, mountings & Rebearing Main Frame | 24
48 | Overhaull Steering Linkage | 8
49 | Install LH & RH Steering cylinder | 4
50 | Install Hyd hose and lines | 48
51 | Install T/Conventer to Engine - completed engine | 24
52 | Install engine Gp To Main Frame | 12
53 | Completed Radiator & Install to Machine | 12
54 | Rebearing A-frame & Install to Rear Axle gp | 9
55 | Install Rear Axle housing | 6
56 | Install LH & RH rear Suspension | 4
57 | Install LH & RH Final drive | 6
58 | Install transmission Gp | 4
59 | Install Rear Axle Shaft LH & RH | 2
60 | Install Rear Tyres | 4
61 | Install Pump to Pump drive & install pump drive Gp to Main Frame | 4
62 | Remove Install Front hub to RF & LF Suspension | 12
63 | Install RH Front Suspension Gp to frame & completed | 6
64 | Install LH Front Suspension Gp to frame & completed | 6
65 | Install Front Tyre LH & RH | 5
66 | Install Fender, catwalk, Hood & guards | 12
67 | Install Air induction & exhaust | 12
68 | Install Hyd & Steering Tank | 4
69 | Install Electric system | 24
70 | Install Fuel tank | 2
71 | Install Fuel lines | 4
72 | Install main drive shaft | 2
73 | Install Pump drive shaft | 1
74 | Install Hyd & Stering Valves | 2
75 | Install Brake Valve & AETA Vlv | 2
76 | Install Accumulator Steering | 4
77 | Install Front Brake & Trans oil cooler | 2
78 | Install Air tank & lines | 4
79 | Install Cabin & Completed | 24
80 | Install Slack Adjuster 2 x | 2
81 | Install Brake airover hyd cyl 3x | 2
82 | Install Mirror, flatform & Handraill | 8
83 | Install Ladders | 4
84 | Install Hoist LH & RH | 4
85 | Completed Machine (include refill oils) | 36
Out Side Work
86 | Repair frame, Guard, handrail etc by SSB | 48
87 | Painting Machine - PT. SHB | 48
88 | GOH Air Conditioner - PT. SEN | 36
89 | GOH Fire supp & Autolube - PT INTECS | 36
Performace test
90 | Performance test | 24
91 | Install guard and hoods | 3
92 | Prerelease | 0.5

## GOH D10T,D10R
No | Job Description GOH D10T/ D10R | Duration (hrs)
Remove / Disassembly
1 | Clean up,remove belly guard,enclosure | 4
2 | Performance test engine & T/conveter, download data PSSR | 6
3 | Blade gp | 4
4 | Stand up machine | 4
5 | Track Gp | 4
6 | Engine hood | 4
7 | Remove battery | 1
8 | Air Intake & Exhaust System | 1
9 | Fuel system & Lines | 3
10 | Cooling system & Lines | 3
11 | Hoist cylinder | 3
12 | Radiator and guard | 3
13 | Drive shaft and coupling | 3
14 | Engine and Torque Converter | 6
15 | Hydraulic tank | 6
16 | Cabin & ROPS | 6
17 | Fuel tank | 6
18 | Aftercooler | 6
19 | Wiring harness | 24
20 | Hydraulic hoses | 24
21 | Remove fender LH & RH | 6
22 | Ripper shank Gp | 3
23 | Ripper cylinder 4X | 3
24 | Transmission Gp | 3
25 | Ripper frame | 3
26 | Fan motor | 1
27 | Fan pump | 1
28 | Trans pump | 1
29 | Hyd & Trans oil cooler | 1
30 | Track frame 2X | 6
31 | Pivot shaft | 4
32 | Equalizer bar | 4
33 | Main Control Valve | 4
34 | Ripper CV | 4
35 | Pilot CV | 4
36 | Final Drive Gp LH & RH | 4
37 | Hydraulic pump | 1
Recondition Component
38 | Recondition LH Hoist Cylinder | 4
39 | Recondition RH Hoist Cylinder | 48
40 | Recondition LH Tilt Cylinder | 2
41 | Recondition RH Tilt Cylinder | 48
42 | Recondition LH Ripper Lift Cylinder | 24
43 | Recondition RH Ripper Lift Cylinder | 16
44 | Recondition RH Ripper Tilt Cylinder | 17
45 | Recondition RH Ripper Tilt Cylinder | 18
46 | Recondition RH Ripper pin puller Cylinder | 19
47 | Recondition Steering clutch control valve | 4
48 | Recondition Main Control valve | 16
Rebearing / reseal Component
49 | Main frame | 16
50 | Ripper Frame | 22
51 | Radiator guard & yoke | 10
52 | Completed Equalizer bar | 8
53 | Inspect Blade gp & Trunnion Repair as condition | 8
54 | Drive shaft and coupling | 3
Assemble Machine
55 | Hyd Hose & lines | 34
56 | Wiring Harness and Electric system | 32
57 | Engine & T/C | 10
58 | Air Intake & Exhaust System | 6
59 | Fuel system & Lines | 4
60 | Cooling system & Lines | 4
61 | Equalizer Bar | 6
62 | Pivot Shaft | 6
63 | Transmission Gp | 4
64 | Ripper Frame | 8
65 | Ripper shank & Pin Puller | 4
66 | Ripper Control Valve | 2
67 | Cyllinder Ripper 4 x | 6
68 | Support Cabin | 4
69 | Fender | 4
70 | Hyd Tank | 4
71 | Final Drive LH & RH | 6
72 | Track Frame x2 | 8
73 | Radiator Gp & Guard | 10
74 | Hoist cylinder 2x | 3
75 | Aftercooler | 2
76 | Fan Motor | 2
77 | Steering control valve | 1
78 | Main control valve | 2
79 | Pilot cotrol valve | 2
80 | Hyd & transnission oil cooler | 1
81 | Drive shaft and coupling | 2
82 | Fan pump | 1
83 | Transmission hoses & lines | 5
84 | Cabin & ROPS +completed | 12
85 | Fuel Tank | 3
86 | Engine hood | 4
87 | Track Gp | 6
88 | Completed machine, refill oil, remove stand etc | 36
89 | Blade gp | 6
Outside Work
90 | Air Cond. by PT. SEN & TU | 24
91 | Autolube & Fire Supp by PT. Intecs | 24
Performace test
92 | Performance test | 24
93 | Install guard and hoods | 3
94 | Prerelease | 1

## GOH ADT 740
No | Job Description GOH ADT 740 | Duration (hrs)
Remove / Disassembly
1 | Clean up machine | 2.5
2 | Take data PSRPT & Performance test | 5
3 | Stand up machine | 4
4 | Remove engine Hood & Radiator guards / hood | 10
5 | Remove Air intake & Exhaust lines | 6
6 | Remove Fuel lines | 2
7 | Remove Main Drive Shaft | 2
8 | Remove pump Drive Shaft | 1
9 | Remove hose & lines | 20
10 | Remove Electric system | 15
11 | Remove Radiator & cooling lines | 6
12 | Remove engine & T/C | 6
13 | Remove Cabin | 4
14 | Remove Mirror, flatform, Handraill & Fender | 12
15 | Remove Front tyre 2 ea | 4
16 | Remove Front LH Suspension Gp | 4
17 | Remove Front RH Suspension Gp | 4
18 | Remove Pump drive | 3
19 | Remove Steering Tank | 2
20 | Remove Air Tank & lines | 2
21 | Remove transmission oil cooler | 4
22 | Remove Rear Tyres | 8
23 | Remove LH & RH Rear Suspension | 4
24 | Remove Rear Axle Shaft LH & RH | 1
25 | Remove LH & RH Final drive | 6
26 | Remove Transmission GP | 4
27 | Remove Rear Axle | 6
28 | Remove Hoist LH & RH | 6
29 | Remove Hyd Tank | 3
30 | Remove Fuel tank | 3
31 | Remove Steering Linkage | 4
32 | Remove Steering cyl LH & RH | 4
33 | Steering valves | 2
34 | Remove acculumator | 2
35 | Brake valves, AETA | 2
36 | Remove Hyd Control valves | 2
37 | Remove front Brake oil cooler | 2
38 | Remove Brake Slack adjuster | 2
39 | Remove Brake airover hyd cyl 3x | 2
40 | Remove Ladders | 4
41 | Clean up main frame | 4
Recondition Component
42 | Discon & connect Transmission & Differential | 3
43 | Recondition Hyd & Trans tank | 6
44 | Recondition Steering Tank | 4
45 | Recondition Fuel Tank | 4
Assemble Machine
46 | Reposition & Stand up main Frame at wshop | 3
47 | Install bracket, mountings & Rebearing Main Frame | 12
48 | Overhaull Steering Linkage | 8
49 | Install LH & RH Steering cylinder | 4
50 | Install Hyd hose and lines | 48
51 | Install T/Conventer to Engine - completed engine | 24
52 | Install engine Gp To Main Frame | 12
53 | Completed Radiator & Install to Machine | 12
54 | Rebearing A-frame & Install to Rear Axle gp | 18
55 | Install Rear Axle housing | 6
56 | Install LH & RH rear Suspension | 4
57 | Install LH & RH Final drive | 6
58 | Install transmission Gp | 4
59 | Install Rear Axle Shaft LH & RH | 2
60 | Install Rear Tyres | 4
61 | Install Pump to Pump drive & install pump drive Gp to Main Frame | 4
62 | Remove Install Front hub to RF & LF Suspension | 12
63 | Install RH Front Suspension Gp to frame & completed | 6
64 | Install LH Front Suspension Gp to frame & completed | 6
65 | Install Front Tyre LH & RH | 5
66 | Install Fender, catwalk, Hood & guards | 12
67 | Install Air induction & exhaust | 12
68 | Install Hyd & Steering Tank | 4
69 | Install Electric system | 36
70 | Install Fuel tank | 2
71 | Install Fuel lines | 4
72 | Install main drive shaft | 2
73 | Install Pump drive shaft | 1
74 | Install Hyd & Stering Valves | 2
75 | Install Brake Valve & AETA Vlv | 2
76 | Install Accumulator Steering | 4
77 | Install Front Brake & Trans oil cooler | 2
78 | Install Air tank & lines | 4
79 | Install Cabin & Completed | 24
80 | Install Slack Adjuster 2 x | 2
81 | Install Brake airover hyd cyl 3x | 2
82 | Install Mirror, flatform & Handraill | 8
83 | Install Ladders | 4
84 | Install Hoist LH & RH | 4
85 | Completed Machine (include refill oils) | 48
86 | Repair frame, Guard, handrail etc by TSP | 60
87 | Painting Machine - PT. SHB | 36
88 | GOH Air Conditioner - PT. SEN | 36
89 | GOH Fire supp & Autolube - PT INTECS | 40
Performace test
90 | Performance test | 36
91 | Install guard and hoods | 3
92 | Prerelease | 0.5