## CompletedJobs
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | title | unit | unit_id | description | status | technician_id | template_id | created_at | started_at | completed_at | paused_at | total_paused_sec | estimated_minutes
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | J10-d64d | Recondition Transmission 16H,G | E448 — D10T | a5c2144b-1b29-40f7-9b5c-cfbbc03c3387 | Job recondition Transmission 16H,G (time frame standar). | done | T-533ca22c | ne-transmission-16h-g | 2026-08-09T09:58:28.026Z | 2026-08-09T09:58:42.998Z | 2026-08-10T08:22:55.264Z |  | 63302 | 10

## CompletedSteps
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | job_id | name | order | status | started_at | completed_at | duration_sec | std_minutes
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 8fb2ce74-0ca5-43f6-9fbc-97dafe62c8e2 | J10-d64d | Dismantle: Washing Transmission gp | 1 | done | 2026-08-09T10:01:58.128Z | 2026-08-09T10:03:03.194Z | 65 | 240
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 13a4ee89-338b-424c-9f78-9310ce7f2607 | J10-d64d | Dismantle: Control Valve 2EA | 2 | done | 2026-08-09T10:03:25.587Z | 2026-08-09T10:05:21.576Z | 115 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | bcf45f80-2bb4-416c-b908-8fd34eb6e2b7 | J10-d64d | Dismantle: Pump, Lines, & Screen | 3 | done | 2026-08-09T10:05:31.817Z | 2026-08-09T10:08:39.129Z | 187 | 240
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5f317f15-e6bc-4f2b-a864-079997807f4b | J10-d64d | Dismantle: Planetary GP | 4 | done | 2026-08-09T10:08:42.805Z | 2026-08-09T10:08:53.272Z | 10 | 900
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | e3403f0f-fe42-4b4c-8cfc-d603d6a4c856 | J10-d64d | Dismantle: Directional & Idler gear | 5 | done | 2026-08-09T10:08:42.805Z | 2026-08-09T10:08:55.236Z | 12 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 64498e18-b6a0-43b9-b73b-3bde88476441 | J10-d64d | Dismantle: Clean up Housing 2ea | 6 | done | 2026-08-09T10:08:55.236Z | 2026-08-09T10:27:58.583Z | 1143 | 120
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | d2b1808c-ec57-42a0-8fe9-9402adde9021 | J10-d64d | Dismantle: Part list & Tear Down | 7 | done | 2026-08-09T10:27:58.583Z | 2026-08-09T10:28:05.839Z | 7 | 240
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5771dcf9-87e3-4dce-8387-0f8bcbdc9fc6 | J10-d64d | Assemble: Directional & Idler gear | 8 | done | 2026-08-09T10:28:05.839Z | 2026-08-09T10:28:08.586Z | 2 | 600
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 2a032ec1-a234-4b0a-9633-9f6b2f92e306 | J10-d64d | Assemble: Planetary GP | 9 | done | 2026-08-09T10:28:08.586Z | 2026-08-09T10:28:15.395Z | 6 | 600
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5db6ba1f-8a71-4d8a-a768-b8ac5fd26d88 | J10-d64d | Assemble: CV 2EA | 10 | done | 2026-08-09T10:28:22.725Z | 2026-08-09T10:35:59.262Z | 456 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5f92ef43-6a78-4f7b-ab04-cd3df9d62ac3 | J10-d64d | Assemble: Pump, Lines, & Screen | 11 | done | 2026-08-09T10:53:30.335Z | 2026-08-09T11:35:16.520Z | 3553 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | edbf8682-f306-41cf-a521-2481624fad10 | J10-d64d | Test Bench & Completed: Set up | 12 | done | 2026-08-09T11:35:16.520Z | 2026-08-09T11:35:53.190Z | 36 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | b59ef223-7b18-410d-b7f5-77b9d3f7a54c | J10-d64d | Test Bench & Completed: Test | 13 | done | 2026-08-09T11:35:53.190Z | 2026-08-09T11:38:08.242Z | 135 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 79648818-9748-43c2-bf0f-0bd9be641b6d | J10-d64d | Test Bench & Completed: Release | 14 | done | 2026-08-09T11:38:08.243Z | 2026-08-09T11:46:23.145Z | 494 | 300
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | f955f167-a492-4b59-b40e-76df4f13143e | J10-d64d | Test Bench & Completed: Completed & Painting | 15 | done | 2026-08-10T08:22:47.469Z | 2026-08-10T08:22:52.725Z | 10889 | 300

## CompletedEvents
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | job_id | type | note | created_at | user_id | user_name | user_level
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 4842ed92-e280-488a-8147-ff39913349ab | J10-d64d | created | Job dibuat dari template Transmission 16H,G | 2026-08-09T09:58:28.026Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 60303a50-b675-40ec-a41b-685400ecfcd1 | J10-d64d | assigned | Diassign ke Hatniansyah | 2026-08-09T09:58:34.735Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 794922dd-ad62-41b2-b6b6-02c090d4fdb6 | J10-d64d | started | Pekerjaan dimulai | 2026-08-09T09:58:42.998Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 3e05979d-9950-4384-81c4-89c348c06ffd | J10-d64d | step_started | Dismantle: Washing Transmission gp | 2026-08-09T10:01:58.128Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | f1011280-0106-441f-932f-e50deeb80dd7 | J10-d64d | step_completed | Dismantle: Washing Transmission gp | 2026-08-09T10:03:03.194Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | d5c3de8b-2c31-4484-a1f2-b5ff8d5abb04 | J10-d64d | step_started | Dismantle: Control Valve 2EA | 2026-08-09T10:03:25.587Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | d68a3e1b-292d-4cb6-b448-a552f95466cc | J10-d64d | step_completed | Dismantle: Control Valve 2EA | 2026-08-09T10:05:21.576Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 08a1b67c-e53e-47ef-ba5a-86dd3a0c736c | J10-d64d | step_started | Dismantle: Pump, Lines, & Screen | 2026-08-09T10:05:31.817Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 138b9b73-889e-45a4-bbeb-b36dd5a76a42 | J10-d64d | step_completed | Dismantle: Pump, Lines, & Screen | 2026-08-09T10:08:39.129Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5ff4e417-6aa2-4f3b-810f-4904e21ae893 | J10-d64d | step_started | Parallel start (2): Dismantle: Planetary GP, Dismantle: Directional & Idler gear | 2026-08-09T10:08:42.805Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | ff87e79b-a69c-4799-8b57-d75b3e9afe1b | J10-d64d | step_completed | Dismantle: Planetary GP | 2026-08-09T10:08:53.272Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 72c8e4b1-94c8-41fc-b816-186eab108604 | J10-d64d | step_completed | Dismantle: Directional & Idler gear | 2026-08-09T10:08:55.236Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5a63cf13-9259-42d6-82dc-756486f8723d | J10-d64d | step_started | Dismantle: Clean up Housing 2ea | 2026-08-09T10:08:55.236Z
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 1a09764a-bae0-4488-a045-42a286cbfeae | J10-d64d | step_completed | Dismantle: Clean up Housing 2ea · oleh Administrator (superuser) | 2026-08-09T10:27:58.583Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5a368314-25db-43c8-8b0d-9ed433c2a50b | J10-d64d | step_started | Dismantle: Part list & Tear Down · oleh Administrator (superuser) | 2026-08-09T10:27:58.583Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 7a412efd-aee9-4a8c-8355-3e60d9e2bbe1 | J10-d64d | step_completed | Dismantle: Part list & Tear Down · oleh Administrator (superuser) | 2026-08-09T10:28:05.839Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | b429a953-4f10-4e9a-a0e8-e733bf6c878e | J10-d64d | step_started | Assemble: Directional & Idler gear · oleh Administrator (superuser) | 2026-08-09T10:28:05.839Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 5c3cd17e-290d-4558-bdc6-23c09ffb4c04 | J10-d64d | step_completed | Assemble: Directional & Idler gear · oleh Administrator (superuser) | 2026-08-09T10:28:08.586Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | dbd88ac5-ada9-459e-9fc7-20045295d9eb | J10-d64d | step_started | Assemble: Planetary GP · oleh Administrator (superuser) | 2026-08-09T10:28:08.586Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | c789feae-3ae1-47ff-a0b9-0b6ef3eac2c9 | J10-d64d | step_completed | Assemble: Planetary GP · oleh Administrator (superuser) | 2026-08-09T10:28:15.395Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 70b1ce2a-f3b0-4492-873c-fe5eda5ecfa9 | J10-d64d | step_started | Assemble: CV 2EA · oleh Administrator (superuser) | 2026-08-09T10:28:22.725Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 0202080d-7eae-4e36-a869-5dd89c5645c7 | J10-d64d | step_completed | Assemble: CV 2EA · oleh Administrator (superuser) | 2026-08-09T10:35:59.262Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | b0b557ba-85b2-4b26-92f8-ac9b6acd0946 | J10-d64d | step_started | Assemble: Pump, Lines, & Screen · oleh Administrator (superuser) | 2026-08-09T10:35:59.262Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 9f332eb1-76f4-4085-ba81-b2953f32f7e7 | J10-d64d | paused | Job dipause · oleh Administrator (superuser) | 2026-08-09T10:53:26.671Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 66fa469a-616d-493b-b15e-0153327c09ef | J10-d64d | resumed | Job dilanjutkan · oleh Administrator (superuser) | 2026-08-09T10:53:30.336Z | U-admin | Administrator | superuser
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 29a082b8-5955-41f8-9a2a-24e46b045159 | J10-d64d | step_completed | Assemble: Pump, Lines, & Screen · oleh foreman (foreman) | 2026-08-09T11:35:16.520Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | c020439a-2343-479e-9f5a-d1322247a3a8 | J10-d64d | step_started | Test Bench & Completed: Set up · oleh foreman (foreman) | 2026-08-09T11:35:16.520Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 0bc6645a-629d-4533-acc0-adc937f6180c | J10-d64d | step_completed | Test Bench & Completed: Set up · oleh foreman (foreman) | 2026-08-09T11:35:53.190Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | e7a74bf6-896e-453b-80fd-25ec0df240aa | J10-d64d | step_started | Test Bench & Completed: Test · oleh foreman (foreman) | 2026-08-09T11:35:53.190Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 6eff98b0-b605-46f2-9608-c9fb8c89263b | J10-d64d | step_completed | Test Bench & Completed: Test · oleh foreman (foreman) | 2026-08-09T11:38:08.243Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 3d6d6add-5aab-494a-a614-480354934ac2 | J10-d64d | step_started | Test Bench & Completed: Release · oleh foreman (foreman) | 2026-08-09T11:38:08.243Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 1d0336b4-6c0b-46ef-86cb-ce62fec7d0ed | J10-d64d | step_completed | Test Bench & Completed: Release · oleh foreman (foreman) | 2026-08-09T11:46:23.145Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | c75f6cfb-b11f-4ce9-9981-c6325ae49f70 | J10-d64d | step_started | Test Bench & Completed: Completed & Painting · oleh foreman (foreman) | 2026-08-09T11:46:23.145Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 16fcae0d-0364-4101-8691-fd2750634121 | J10-d64d | updated | Job diubah · oleh foreman (foreman) | 2026-08-09T12:51:33.663Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 1b36b2c9-3317-41bc-9804-e1e8c820e4cb | J10-d64d | paused | Job dipause · oleh foreman (foreman) | 2026-08-09T14:47:48.108Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | af4e3cc2-af04-4d29-96e3-396dbcb72fe6 | J10-d64d | resumed | Job dilanjutkan · oleh foreman (foreman) | 2026-08-10T08:22:47.469Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | ebf237bb-d118-406a-9a45-c47f43e159b1 | J10-d64d | step_completed | Test Bench & Completed: Completed & Painting · oleh foreman (foreman) | 2026-08-10T08:22:52.725Z | U-e83ecb66 | foreman | foreman
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 82dd5f7a-0921-4f1f-b1fb-08f7c8b71995 | J10-d64d | completed | Job selesai · oleh foreman (foreman) | 2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman

## CompletedAssignees
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | job_id | technician_id | technician_name | technician_sn | assigned_at | is_lead
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | 698976bd-9c90-49cf-bc91-fd2a13f3b2bd | J10-d64d | T-533ca22c | Hatniansyah | 3348 | 2026-08-09T09:58:34.735Z | 1

## CompletedHandovers
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | job_id | order | title | done | note | user_id | user_name | updated_at
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | af9992e8-f013-48e6-bbc0-98946e5dfc32 | J10-d64d | 1 | Test Handover over | 1 |  | U-e83ecb66 | foreman | 2026-08-09T12:55:42.573Z

## CompletedPartLoans
archived_at | archived_by_user_id | archived_by_user_name | archived_by_user_level | id | job_id | order | part_name | status | note | user_id | user_name | updated_at
2026-08-10T08:22:55.264Z | U-e83ecb66 | foreman | foreman | ae2694b3-1713-4add-b31a-1783efc39d71 | J10-d64d | 1 | PN 1 | closed | Test | U-e83ecb66 | foreman | 2026-08-09T12:55:32.221Z