## Engine 3306
Unit No : SN : Comp : Engine 3306 |  | SO | WIP: | Actual Labor: |  | Remaining Labor | 0 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Man Power | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [11 empty] | 0
| 2025-06-19 | Receipt by Planner | [10 empty] | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  |  | 0 | Rahmat | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  |  | 0 | Rahmat | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  |  | 0 | Rahmat | FALSE
| 2025-06-20 | Open work order | [10 empty] | 0 | Doni | FALSE
|  | Tag component | [10 empty] | 0 | Rahmat | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  |  | 0 | Yudhistira | FALSE
2 | Disassemble | [11 empty] | 0
|  | Moving component | [6 empty] | 1 | 1 |  |  | 0 | Rahmat | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 10 |  |  | 0 | Rahmat, irwan | FALSE
|  | Disassembly and cleaning small components as follows : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Irwan | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 2 |  |  | 0 | Irwan | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Irwan | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Rahmat | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Rahmat | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Rahmat | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Rahmat | FALSE
|  | -Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors |  | 6 | EA |  |  |  | 2 | 2 |  |  | 0 | Rahmat | FALSE
|  | Apply contamination control | [10 empty] | 0 | Rahmat | FALSE
|  | Failure analysis if required. | [10 empty] | 0 |  | FALSE
3 | Inspect and Measure | [11 empty] | 0
|  | Visually inspect parts | [6 empty] | 2 | 4 |  |  | 0 | Rahmat | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 4 |  |  | 0 | Irwan | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 2 |  |  | 0 | Rahmat | FALSE
|  | Compare against resuability guides | [6 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [10 empty] | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Planer | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [10 empty] | 0 | Technician
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 1 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 7 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - FIP & Nozzle. |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0
|  | Test preparation | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 14 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.
Note on Q34: Herman: 23/06/2025 submit ccr & abnormal parts

## Engine 3406
Unit No : SN : Comp : Engine 3406 |  | SO : | WIP: | Actual Labor: | 0 | Remaining Labor | 0 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Man Power | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive
|  | Receipt by Planner | [10 empty] | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Open work order | [10 empty] | 0 | Planer | FALSE
|  | Tag component | [10 empty] | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  |  | 0 | Technician | FALSE
2 | Disassemble | [11 empty] | 0
|  | Moving component | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Disassembly and cleaning small components as follows : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | -Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Nozzle |  | 6 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Apply contamination control | [10 empty] | 0 | Technician | FALSE
|  | Failure analysis if required. | [10 empty] | 0 |  | FALSE
3 | Inspect and Measure | [11 empty] | 0
|  | Visually inspect parts | [6 empty] | 2 | 4 |  |  | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 4 |  |  | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Compare against resuability guides | [6 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [10 empty] | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Herman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Herman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Planer | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [10 empty] | 0 | Technician
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 1 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 7 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors. |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0
|  | Test preparation | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 14 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.
Note on Q34: Herman: 23/06/2025 submit ccr & abnormal parts

## Engine 3412
Unit No : SN : 38S24696 Comp : Engine 3412 |  | SO : | WIP: | Actual Labor | 0 | Remaining Labor | 0 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Men | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [11 empty] | 0
|  | Receipt by Planner | [10 empty] | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Open work order | [10 empty] | 0 | Planer | FALSE
|  | Tag component | [10 empty] | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  |  | 0 | Technician | FALSE
2 | Disassemble | [11 empty] | 0
|  | Moving component | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 47 |  |  | 0 | Technician | FALSE
|  | Disassembly and cleaning small components as follows : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 2 | EA |  |  |  | 1 | 2 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 1 | 2 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Nozzle |  | 12 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Apply contamination control | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Failure analysis if required. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
3 | Inspect and Measure | [11 empty] | 0 |  | FALSE
|  | Visually inspect parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 5 |  |  | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Compare against resuability guides | [6 empty] | 1 | 8 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [10 empty] | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Planer | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 8 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [6 empty] | 2 | 30 |  |  | 0 | Technician
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 2 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Nozzle |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0
|  | Test preparation | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.

## Egnine C9
Unit No : SN : Comp : Engine C-9 |  | SO : | WIP: | 0 | Actual Labor: | 0 | Remaining Labor | 0 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging | 0
Eight Component Rebuild Sub-Processes |  |  |  |  | Component Storage |  |  |  |  | Men | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [12 empty] | 0
|  | Receipt by Planner | [11 empty] | 0 | Planer | FALSE
|  | Unpacking | [7 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Pre-inspection for condition and missing parts | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Photograph component. | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Open work order | [11 empty] | 0 | Planer | FALSE
|  | Tag component | [11 empty] | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [7 empty] | 1 | 6 |  |  | 0 | Technician | FALSE
2 | Disassemble | [12 empty] | 0
|  | Moving component | [7 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Disassembly engine and cleaning of all parts | [7 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Disassembly and cleaning small components as follows : | [11 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  |  | 2 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Cylinder block |  |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Conrod |  |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | -Fan drive |  |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors |  |  | 6 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Apply contamination control | [11 empty] | 0 | Technician | FALSE
|  | Failure analysis if required. | [11 empty] | 0 | Technician | FALSE
3 | Inspect and Measure | [12 empty] | 0
|  | Visually inspect parts | [7 empty] | 2 | 4 |  |  | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [7 empty] | 2 | 4 |  |  | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Compare against resuability guides | [7 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [11 empty] | 0 | Planer | FALSE
4 | Quotation | [12 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [11 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [11 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [11 empty] | 0 | Part dept | FALSE
|  | Complete quote | [11 empty] | 0 | Planer | FALSE
|  | Customer approval | [11 empty] | 0 | sales | FALSE
5 | Parts Order | [12 empty] | 0
|  | Enter order into system | [11 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [11 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [11 empty] | 0 | Planer | FALSE
|  | Part receiving | [7 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [12 empty] | 0
|  | Verify correct parts | [7 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [7 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [11 empty] | 0 | Technician
|  | Assemble components as follow : | [11 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  |  | 1 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  |  | 6 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  |  | 1 | EA |  |  |  | 2 | 7 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors. |  |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [12 empty] | 0
|  | Test preparation | [7 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [7 empty] | 2 | 14 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
8 | Paint | [12 empty] | 0
|  | Plug and cover | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [7 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [7 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [7 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [12 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [7 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [7 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [9 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.

## Engine C13
Unit No : SN : R9H Comp : Engine C13 |  | SO : | WIP: | Actual Labor: | 0 | Remaining Labor | 0 | Progress Dismantle | 100% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Men | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [11 empty] | 0
|  | Receipt by Planner | [9 empty] | 0 | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  | 0 | 0 | Technician | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  | 0 | 0 | Technician | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  | 0 | 0 | Technician | FALSE
|  | Open work order | [9 empty] | 0 | 0 | Planer | FALSE
|  | Tag component | [9 empty] | 0 | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  | 0 | 0 | Technician | FALSE
2 | Disassemble | [11 empty] | 0
|  | Moving component | [6 empty] | 1 | 1 | N | 0 | 0 | Technician | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 10 |  | 0 | 0 | Technician | FALSE
|  | Disassembly and cleaning small components as follows : | [9 empty] | 0 | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  | 0 | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  | 0 | 0 | Technician | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 5 |  | 0 | 0 | Technician | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 8 |  | 0 | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | -Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | - ECM and Injectors |  | 6 | EA |  |  |  | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | Apply contamination control | [9 empty] | 0 | 0 | Technician | FALSE
|  | Failure analysis if required. | [9 empty] | 0 | 0 | Technician | FALSE
3 | Inspect and Measure | [11 empty] | 0
|  | Visually inspect parts | [6 empty] | 2 | 4 |  | 0 | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 4 |  | 0 | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 2 |  | 0 | 0 | Technician | FALSE
|  | Compare against resuability guides | [6 empty] | 2 | 2 |  | 0 | 0 | Technician | FALSE
|  | Check for product updates | [9 empty] | 0 | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Planer | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [10 empty] | 0 | Technician
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 1 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 6 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 1 | EA |  |  |  | 2 | 7 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors. |  | 6 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0
|  | Test preparation | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 14 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.
Note on Q34: Herman: 23/06/2025 submit ccr & abnormal parts

## Engine C27
Unit No : SN : Comp : Engine C27 |  | SO : | WIP: | Actual Labor |  | Remaining Labor | 0 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Man power | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [11 empty] | 0
|  | Receipt by Planner | [10 empty] | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Open work order | [10 empty] | 0 | Planer | FALSE
|  | Tag component | [10 empty] | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  |  | 0 | Technician | FALSE
2 | Disassemble | [11 empty] | 0
|  | Moving component | [6 empty] | 1 | 1 |  |  | 0 | Technician | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 47 |  |  | 0 | Technician | FALSE
|  | Disassembly and cleaning small components as follows : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  |  | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 2 | EA |  |  |  | 1 | 2 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 1 | 2 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | -Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors |  | 12 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | Apply contamination control | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Failure analysis if required. | [6 empty] | 1 | 4 |  |  | 0 |  | FALSE
3 | Inspect and Measure | [11 empty] | 0
|  | Visually inspect parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 5 |  |  | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Compare against resuability guides | [6 empty] | 1 | 8 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [5 empty] | y |  |  |  |  | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Planer | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 8 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [6 empty] | 2 | 30 |  |  | 0 | Technician
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 2 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors. |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0
|  | Test preparation | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 0
Hours are for service directs only, those who book time to the work order.

## Engine 3412 E
Unit No : SN : 7KK00299 Comp : Engine 3412E |  | SO : | WIP: | Actual Labor | 0 | Remaining Labor | 527 | Progress Dismantle | 0% | Part Progress | 0% | Assemble progress | 0% | Aging
Eight Component Rebuild Sub-Processes |  |  |  | Component Storage |  |  |  |  | Men | Std Hours | Shifts | Actual hrs | Total | Who ( Name ) | if job done please klik on box
1 | Receive | [11 empty] | 0
|  | Receipt by Planner | [10 empty] | 0 | Planer | FALSE
|  | Unpacking | [6 empty] | 1 | 1 |  |  | 0 | Maulana | FALSE
|  | Pre-inspection for condition and missing parts | [6 empty] | 1 | 2 |  |  | 0 | Maulana | FALSE
|  | Photograph component. | [6 empty] | 1 | 2 |  |  | 0 | Maulana | FALSE
|  | Open work order | [10 empty] | 0 | Doni | FALSE
|  | Tag component | [10 empty] | 0 | Technician | FALSE
|  | Compile abnormal part list and CCR | [6 empty] | 1 | 6 |  |  | 0 | Technician | FALSE
2 | Disassemble | [11 empty] | 0 |  | FALSE
|  | Moving component | [6 empty] | 1 | 1 |  |  | 0 | Maulana | FALSE
|  | Disassembly engine and cleaning of all parts | [6 empty] | 2 | 47 |  |  | 0 | Maulana | FALSE
|  | Disassembly and cleaning small components as follows : | [10 empty] | 0 | Maulana | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 2 |  |  | 0 | Technician | FALSE
|  | - Cylinder block |  | 1 | EA |  |  |  | 2 | 8 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 1 | EA |  |  |  | 1 | 2 |  |  | 0 | Maulana | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 1 | 2 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Maulana | FALSE
|  | -Fan drive |  | 1 | EA |  |  |  | 2 | 2 |  |  | 0 | Maulana | FALSE
|  | - ECM and Injectors |  | 12 | EA |  |  |  | 2 | 2 |  |  | 0 | Maulana | FALSE
|  | Apply contamination control | [6 empty] | 2 | 10 |  |  | 0 | Technician | FALSE
|  | Failure analysis if required. | [6 empty] | 1 | 4 |  |  | 0 |  | FALSE
3 | Inspect and Measure | [11 empty] | 0 |  | FALSE
|  | Visually inspect parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Measure and record facts & Photograph parts for reports | [6 empty] | 2 | 5 |  |  | 0 | Technician | FALSE
|  | NTD Testing (crack testing). | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Compare against resuability guides | [6 empty] | 1 | 8 |  |  | 0 | Technician | FALSE
|  | Check for product updates | [10 empty] | 0 | Planer | FALSE
4 | Quotation | [11 empty] | 0 |  | FALSE
|  | Prepare Service Parts Requisition (SPR). | [10 empty] | 0 | Foreman | FALSE
|  | Check parts availability. | [10 empty] | 0 | Foreman | FALSE
|  | Parts pricing | [10 empty] | 0 | Part dept | FALSE
|  | Complete quote | [10 empty] | 0 | Doni | FALSE
|  | Customer approval | [10 empty] | 0 | sales | FALSE
5 | Parts Order | [11 empty] | 0 |  | FALSE
|  | Enter order into system | [10 empty] | 0 | Planer | FALSE
|  | Follow-up back orders | [10 empty] | 0 | Planer | FALSE
|  | Part collection / delivery | [10 empty] | 0 | Planer | FALSE
|  | Part receiving | [6 empty] | 0 |  |  |  | 0 | Planer | FALSE
6 | Assemble | [11 empty] | 0 |  | FALSE
|  | Verify correct parts | [6 empty] | 1 | 5 |  |  | 0 | Technician | FALSE
|  | Final clean / confirm cc control | [6 empty] | 2 | 8 |  |  | 0 | Technician | FALSE
|  | Assemble engine, follow procedures | [6 empty] | 2 | 30 |  |  | 0 | Technician | FALSE
|  | Assemble components as follow : | [10 empty] | 0 | Technician | FALSE
|  | - Crankshaft |  | 1 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Camshaft |  | 2 | EA |  |  |  | 2 | 3 |  |  | 0 | Technician | FALSE
|  | - Conrod |  | 12 | EA |  |  |  | 2 | 6 |  |  | 0 | Technician | FALSE
|  | - Cylinder head |  | 2 | EA |  |  |  | 2 | 12 |  |  | 0 | Technician | FALSE
|  | - Turbocharger |  | 2 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Water Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - Oil Pump |  | 1 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
|  | - ECM and Injectors. |  | 12 | EA |  |  |  | 2 | 5 |  |  | 0 | Technician | FALSE
7 | Test and Adjust | [11 empty] | 0 |  | FALSE
|  | Test preparation | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Bench test performance | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
|  | Install on proper stand | [6 empty] | 2 | 11 |  |  | 0 | Technician | FALSE
8 | Paint | [11 empty] | 0 |  | FALSE
|  | Plug and cover | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Clean and prepare for painting | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Paint | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Install component ID tag. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
|  | Final inspection. | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
|  | Shrink wrap. | [6 empty] | 1 |  |  |  | 0 | Technician | FALSE
9 | Completing plug and play parts | [11 empty] | 0 |  | FALSE
|  | Installation other attachments such as V-belts, Alternator, Starting motor, AC compressor, Air cleaner, Heat Shields, etc.. | [6 empty] | 1 | 4 |  |  | 0 | Technician | FALSE
|  | Retorque bolt after dyno test | [6 empty] | 1 | 2 |  |  | 0 | Technician | FALSE
Notes | [8 empty] | Total Hours |  |  |  | 527
Hours are for service directs only, those who book time to the work order.